## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | Investor
1.1 | Investor Model |  | Omar Khaled
1.2 | Create Investor | 5 | Omar Khaled | Investor Model | Post on Postman
1.3 | Read Investor | 3 | Omar Khaled | Investor Model | Get on Postman
1.4 | Update Investor | 13 | Omar Khaled | Investor Model | Put on Postman
1.5 | Delete Investor | 8 | Omar Khaled | Investor Model | delete on Postman
2 | SSCManager
2.1 | SSCManager Model |  | Nada Abdelmonem
2.2 | Create SSCManager | 5 | Nada Abdelmonem | SSCManager Model | Post on Postman
2.3 | Read SSCManager | 3 | Nada Abdelmonem | SSCManager Model | Get on Postman
2.4 | Update SSCManager | 13 | Nada Abdelmonem | SSCManager Model | Put on Postman
2.5 | Delete SSCManager | 8 | Nada Abdelmonem | SSCManager Model | delete on Postman
3 | SSCForm
3.1 | SSCForm Model |  | Nadine Mostafa
3.2 | Create SSCForm | 5 | Nadine Mostafa | SSCForm Model | Post on Postman
3.3 | Read SSCForm | 3 | Nadine Mostafa | SSCForm Model | Get on Postman
3.4 | Update SSCForm | 13 | Nadine Mostafa | SSCForm Model | Put on Postman
3.5 | Delete SSCForm | 8 | Nadine Mostafa | SSCForm Model | delete on Postman
4 | SPCForm
4.1 | SPCForm Model |  | Youssr Abou-Youssif
4.2 | Create SPCForm | 5 | Youssr Abou-Youssif | SPCForm Model | Post on Postman
4.3 | Read SPCForm | 3 | Youssr Abou-Youssif | SPCForm Model | Get on Postman
4.4 | Update SPCForm | 13 | Youssr Abou-Youssif | SPCForm Model | Put on Postman
4.5 | Delete SPCForm | 8 | Youssr Abou-Youssif | SPCForm Model | delete on Postman
5 | Lawyer
5.1 | Lawyer Model |  | Mohamed Amr
5.2 | Create Lawyer | 5 | Mohamed Amr | Lawyer Model | Post on Postman
5.3 | Read Lawyer | 3 | Mohamed Amr | Lawyer Model | Get on Postman
5.4 | Update Lawyer | 13 | Mohamed Amr | Lawyer Model | Put on Postman
5.5 | Delete Lawyer | 8 | Mohamed Amr | Lawyer Model | delete on Postman
6 | Reviewer
6.1 | Reviewer Model |  | Ali Ibrahim
6.2 | Create Reviewer | 5 | Ali Ibrahim | Reviewer Model | Post on Postman
6.3 | Read Reviewer | 3 | Ali Ibrahim | Reviewer Model | Get on Postman
6.4 | Update Reviewer | 13 | Ali Ibrahim | Reviewer Model | Put on Postman
6.5 | Delete Reviewer | 8 | Ali Ibrahim | Reviewer Model | delete on Postman
7 | Admin
7.1 | Admin Model |  | Abdelrahman Adel
7.2 | Create Admin | 5 | Abdelrahman Adel | Admin Model | Post on Postman
7.3 | Read Admin | 3 | Abdelrahman Adel | Admin Model | Get on Postman
7.4 | Update Admin | 13 | Abdelrahman Adel | Admin Model | Put on Postman
7.5 | Delete Admin | 8 | Abdelrahman Adel | Admin Model | delete on Postman
8 | Case
8.1 | Case Model |  | Nada Labib
8.2 | Create Case | 5 | Nada Labib | Case Model | Post on Postman
8.3 | Read Case | 3 | Nada Labib | Case Model | Get on Postman
8.4 | Update Case | 13 | Nada Labib | Case Model | Put on Postman
8.5 | Delete Case | 8 | Nada Labib | Case Model | delete on Postman
9 | Company
9.1 | Company Model |  | Rodayna Ehab
9.2 | Create Company | 5 | Rodayna Ehab | Company Model | Post on Postman
9.3 | Read Company | 3 | Rodayna Ehab | Company Model | Get on Postman
9.4 | Update Company | 13 | Rodayna Ehab | Company Model | Put on Postman
9.5 | Delete Company | 8 | Rodayna Ehab | Company Model | delete on Postman
10 | Server Side | 8 | Omar Khaled |  | Run from cmd