## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | Case
1.1 | Model | 1 | Nada Labib | Rodayna Ehab | Youssr AbouYoussif
1.2 | Validations | 1 | Nada Labib | Rodayna Ehab | Youssr AbouYoussif
1.3 | CRUDS | 2 | Nada Labib | Rodayna Ehab | Youssr AbouYoussif
2 | Form
2.1 | Model | 3 | Rodayna Ehab | Nadine Moustafa | Nada Labib
2.2 | Validations | 2 | Nadine Moustafa | Mohamed Amr | Nada Labib
2.3 | CRUDS
2.3.1 | Create | 5 | Nadine Moustafa | Nada Labib | Omar Khaled
2.3.2 | Read | 2 | Nada AbdelMonem | Nada Labib | Youssr AbouYoussif
2.3.3 | Update,Delete | 2 | Youssr AbouYoussif | Rodayna Ehab | Nadine Moustafa
3 | Admin
3.1 | Model | 1 | Abdelrahman Adel | Nada AbdelMonem | Youssr AbouYoussif
3.2 | Validations | 1 | Abdelrahman Adel | Nada AbdelMonem | Youssr AbouYoussif
3.3 | CRUDS | 2 | Abdelrahman Adel | Nada AbdelMonem | Youssr AbouYoussif
4 | User
4.1 | Model | 3 | Ali ElSebaie | Mohamed Amr | Omar Khaled
4.2 | Validations
4.2.1 | Create Validations | 2 | Ali ElSebaie | Mohamed Amr | Omar Khaled
4.2.2 | Update Validations | 2 | Mohamed Amr | Rodayna Ehab | Youssr AbouYoussif
4.3 | CRUDS | 3 | Omar Khaled | Mohamed Amr | Ali ElSebaie
5 | Sorting the cases
5.1 | As a lawyer/reviewer I should be able to sort the cases by case ID | 3 | Ali ElSebaie | Nada Labib | Nada AbdelMonem
5.2 | As a lawyer/reviewer I should be able to sort the cases by creation date | 3 | Mohamed Amr | Rodayna Ehab | Youssr AbouYoussif
5.3 | As an admin I should be able to sort the cases by case ID | 3 | Abdelrahman Adel | Omar Khaled | Rodayna Ehab
5.4 | As an admin I should be able to sort the cases by creation date | 3 | Omar Khaled | Nada Labib | Nada AbdelMonem
6 | Accepting or rejecting a form (we will follow this by updating the boolean attribute>> lawyerApproval or reviewerApproval to true or false)
6.1 | As a lawyer/reviewer I should be able to get the form from the case | 3 | Youssr AbouYoussif | Nada Labib | Nada AbdelMonem
6.2 | As a lawyer/reviewer I should be able to get a certain case | 3 | Nada Labib | Nada AbdelMonem | Rodayna Ehab
7 | Adding attribute called ''financial balance" in User model |  | Rodayna Ehab
7.1 | As an investor I should be able to get my financial balance | 2 | Rodayna Ehab | Youssr AbouYoussif | Ali ElSebaie
8 | Search for a company by its name
8.1 | As an admin I should be able to get a case by company name | 3 | Nada AbdelMonem | Youssr AbouYoussif | Nada Labib
9 | Viewing Comments
9.1 | As a lawyer I should be able to view the reviewer’s comments | 2 | Nada AbdelMonem | Nadine Moustafa | Nada Labib