## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | User
1.1 | Read
1.1.1 | Controller get | 2 | Ali El-Sebaie | Nada Labib | Abdelrahman Adel
1.1.2 | Test Get a certain user | 5 | Ali El-Sebaie | Nada Labib | Abdelrahman Adel
1.1.3 | Test Get all users |  | Ali El-Sebaie | Nada Labib | Abdelrahman Adel
1.1.4 | Test Get financial balance of an investor |  | Ali El-Sebaie | Nada Labib | Abdelrahman Adel
1.1.5 | Test Get the form of a lawyer/reviewer |  | Ali El-Sebaie | Nada Labib | Abdelrahman Adel
1.2 | Delete
1.2.1 | Controller delete | 2 | Mohamed Amr | Nada Labib | Abdelrahman Adel
1.2.2 | Test Delete a ceratin user | 5 | Mohamed Amr | Nada Labib | Abdelrahman Adel
1.3 | Create
1.3.1 | Controller Create | 2 | Mohamed Amr | Nadine Moustafa | Nada AbdelMonem
1.3.2 | Test Create a certain user | 5 | Mohamed Amr | Nadine Moustafa | Nada AbdelMonem
1.4 | Update
1.4.1 | Controller Update | 2 | Ali El-Sebaie | Nadine Moustafa | Nada AbdelMonem
1.4.2 | Test update a certain user | 5 | Ali El-Sebaie | Nadine Moustafa | Nada AbdelMonem
1.5 | Sorting
1.5.1 | Test Sort case by ID | 5 | Nada AbdelMonem | Youssr Abou-Youssif | Abdelrahman Adel
1.6 | Login | 8 | Rodayna Ehab | Nadine Moustafa | Mohamed Amr
1.6.1 | Test login | 5 | Rodayna Ehab | Nadine Moustafa | Mohamed Amr
2 | Form
2.1 | Read
2.1.1 | Controller get | 2 | Nadine Moustafa | Omar Khaled | Mohamed Amr
2.1.2 | Test Get all Forms/by id | 5 | Nadine Moustafa | Omar Khaled | Mohamed Amr
2.2 | Delete
2.2.1 | Controller delete | 2 | Nadine Moustafa | Omar Khaled | Mohamed Amr
2.2.2 | Test Delete a certain Form | 5 | Nadine Moustafa | Omar Khaled | Mohamed Amr
2.3 | Update
2.3.1 | Controller update | 2 | Youssr Abou-Youssif | Ali El-Sebaie | Nada AbdelMonem
2.4 | Create
2.4.1 | Controller Create | 2 | Youssr Abou-Youssif | Ali El-Sebaie | Nada AbdelMonem
2.5 | Validations
2.5.1 | Update validations | 5 | Rodayna Ehab | Nadine Mousatfa | Mohamed Amr
3 | Admin
3.1 | Read
3.1.1 | Test Get all admins/certain admin | 5 | Abdelrahman Adel | Rodayna Ehab | Omar Khaled
3.1.2 | Controller get | 2 | Rodayna Ehab | Nadine Mousatfa | Mohamed Amr
3.2 | Delete
3.2.1 | Controller Delete | 2 | Abdelrahman Adel | Rodayna Ehab | Omar Khaled
3.2.2 | Test Delete a certain admin | 5 | Abdelrahman Adel | Rodayna Ehab | Omar Khaled
3.3 | Create
3.3.1 | Controller Create | 2 | Rodayna Ehab | Nadine Mousatfa | Mohamed Amr
3.3.2 | Test Create a certain admin | 5 | Rodayna Ehab | Nadine Mousatfa | Mohamed Amr
3.4 | Update
3.4.1 | Controller update | 2 | Abdelrahman Adel | Rodayna Ehab | Omar Khaled
3.4.2 | Test Update a certain admin | 5 | Abdelrahman Adel | Rodayna Ehab | Omar Khaled
3.5 | Sorting
3.5.1 | Test Sort case by creation date | 5 | Abdelrahman Adel | rodayna Ehab | Omar Khaled
4 | As a lawyer I can add lawyer/reviewer comments | 5 | Nada Labib | Ali El-Sebaie | Rodayna Ehab
4.1 | Test as a lawyer I can add lawyer/reviewer comments | 5 | Nada labib | Ali El-Sebaie | Rodayna Ehab
5 | Test as an admin I can get a form by company name | 5 | Nada Labib | Ali El-Sebaie | Rodayna Ehab
6 | As an investor I can view my companies page /As a user I can view my pending cases | 5 | Youssr Abou-Youssif | Ali El-Sebaie | Nada AbdelMonem
6.1 | Test As an investor I can view my companies page /As a user I can view my pending cases | 5 | Youssr Abou-Youssif | Ali El-Sebaie | Nada AbdelMonem
7 | Register in admins/users | 8 | Mohamed Amr | Nada Labib | Abdelrhaman Adel
7.1 | Test register in admins/users | 5 | Mohamed Amr | Nada Labib | Abdelrhaman Adel
8 | Delete a form from user | 5 | Omar Khaled | Youssr Abou-Youssif | Mohamed Amr
9 | Create a form from user | 8 | Nada AbdelMonem | Youssr Abou-Youssif | Abdelrahman Adel
9.1 | Test create a form from user | 5 | Nada AbdelMonem | Youssr Abou-Youssif | Abdelrahman Adel
10 | Update a form from a certain user | 5 | Ali El-Sebaie | Nada Labib | Abdelrahman Adel
10.1 | Test update a form from a certain user | 5 | Ali El-Sebaie | Nada Labib | Abdelrahman Adel
11 | Notifications
11.1 | Investor should be notified about any update in his cases | 21 | Omar Khaled | Youssr Abou-Youssif | Mohamed Amr
11.2 | Test Investor should be notified about any update in his cases | 5 | Omar Khaled | Youssr Abou-Youssif | Mohamed Amr
12 | Added a new Entity "External Entity" | 8 | Nadine Moustafa
12.1 | Models |  | Nadine Moustafa | Omar Khaled | Mohamed Amr
12.2 | CRUD operations |  | Nadine Moustafa | Omar Khaled | Mohamed Amr
12.3 | Validations |  | Nadine Moustafa | Omar Khaled | Mohamed Amr
12.4 | Controllers |  | Nadine Moustafa | Omar Khaled | Mohamed Amr
12.5 | Test delete an external entity | 5 | Nadine Moustafa | Omar Khaled | Mohamed Amr
12.6 | Test create an external entity | 5 | Nada Labib | Ali El-Sebaie | Rodayna Ehab
12.7 | Test update an external entity | 5 | Youssr Abou-Youssif | Ali El-Sebaie | Nada AbdelMonem
12.8 | Test get all external entities/ by id | 5 | Youssr Abou-Youssif | Ali El-Sebaie | Nada AbdelMonem
12.9 | Test get external entity by name/by Api | 5 | Nada Labib | Omar Khaled | Mohamed Amr
13 | Test review comments as a lawyer/reviewer | 3+3=6 | Nada AbdelMonem | Youssr Abou-Youssif | Abdelrahman Adel
15 | Merging case into form | 2 | Youssr Abou-Youssif | Ali El-Sebaie | Nada AbdelMonem